SUBCONTRACT AGREEMENT

Greater Southwest Constructors, Inc.

P.O. Box 834

Weatherford, Texas 76086

Phone (817) 596-3213

Fax (817) 596-3513

CONTRACTOR:	Greater Southwest Constructors, Inc.

SUBCONTRACTOR:	Ed Parker , Inc.

OWNER:	Lockheed Martin

CONTRACT #:	H24-0605

EFFECTIVE DATE:	5/21/2007

SUBCONTRACT PRICE:	$299126.00

TWO HUNDRED NINTY NINE THOUSAND ONE HUNDRED TWENTY SIX DOLLARS AND NO /100 CENTS

PROGRESS REPORT LIQUIDATED DAMAGE AMOUNT:	$100.00

PROGRESS CONFERENCE LIQUIDATED DAMAGE AMOUNT:	$100.00

DELAY LIQUIDATED DAMAGE AMOUNT:	$100.00

MONTHLY PAYMENT APPLICATION DATE: PERIOD ENDING 25TH OF EACH MONTH.INVOICE INCLUDING % OF COMPLETION PER SCHEDULE OF VALUES DUE PRIOR TO THE 20TH OF EACH MONTH.

PROJECT:	Fuel Filter Area Bldg.211

Cost Category:	16-100-100

This Subcontract Agreement (herein called "Agreement") is made and entered into as of the "Effective Date" (herein so called) listed above, by and between Greater Southwest Constructors, Inc. (herein called "Contractor"), and the "Subcontractor" (herein so called) listed above, for the performance of the "Subcontract Work" (as that term is defined above) on the "Project" (herein so called) listed above. If the "Contract" (herein so called) referenced above is a prime contract between the owner of the "Project" (herein so called) listed above and the Contractor, then the term "Owner" refers to that owner. If the Contract is itself a subcontract, then the term "Owner" refers to the party to the Contract with which Contractor is in privity. Both the Contractor and Subcontractor agree to perform each's respective obligations as set forth below and in the attached Exhibits, to wit:

ARTICLE I

SCOPE OF WORK

1.01	Subcontract Work. Subcontractor shall furnish all labor, materials, fuel, equipment, tools, machinery, and supplies; perform all work; obtain all necessary permits; pay all state sales taxes, state and federal unemployment taxes, and all other taxes and fees associated with the subcontract labor or materials; provide all required construction layout and surveying; and do all things necessary to complete the work described on Exhibit "A," attached hereto and incorporated herein (herein called the "Subcontract Work"), together with all appurtenant and related work in strict compliance with the "Contract Documents" (herein so called) described in Section 1.02, below.

1.02	Contract Documents.

(a)	The Contract Documents shall include, in addition to this Agreement, all documents (including the Contract) reflecting the agreement between the Owner and the Contractor for the Project, the "Project Schedule" (herein so called) provided by Contractor, the "Special Provisions" (herein so called) listed on Exhibit "C," attached hereto and incorporated herein, the "Work scope Clarifications" (herein so called) listed on Exhibit "D," attached hereto and incorporated herein, the plans, specifications, general conditions, special conditions, addenda, performance bond and/or payment bond, if any, and all documents listed in Exhibit "B", attached hereto and incorporated herein.

(b)	Subcontractor acknowledges having read each of the Contract Documents described in paragraph (a), immediately above, and is familiar with each and every part thereof affecting the Subcontract Work. Subcontractor by examination has satisfied itself as to the nature and location of the Subcontract Work; the character, quantity, and kinds of materials necessary; the adequacy of any surface or subsurface conditions necessary to assure proper installation of the Subcontract Work; the kinds and quantity of equipment needed; and other local conditions or matters affecting compliance with the Contract Documents. Further, Subcontractor is familiar with the respective rights, powers, benefits, and liabilities of the Contractor and the Owner under the Contract and hereby agrees (i) to comply therewith insofar as same are applicable to the Subcontract Work, and (ii) to perform all provisions thereof which are applicable to the Subcontract Work.

(c)	Any questions arising with respect to interpretation of the Contract Documents or any related drawings, plans, or specifications shall be submitted through the Contractor; and the Subcontractor shall follow the directions of the Owner or the Owner's representative, as conveyed by the Contractor, with respect to such matters. The Subcontractor agrees that the Owner's (or its representative's) interpretation of the requirements of the Contract Documents and its decision in matters relating to artistic effect shall be final, as long as such interpretation and/or decision is not in conflict with the terms of the Contract Documents.

(d)	The Subcontractor agrees to be bound to the Contractor under this Agreement according to the same terms and conditions as the Contractor is bound to the Owner under the Contract. The Subcontractor shall assume and perform all of the obligations and responsibilities of the Contractor under the Contract, which pertain or relate to the scope of the Subcontract Work as described in Section 1.01.

ARTICLE II

PERFORMANCE AND PROSECUTION OF WORK

2.01	Independent Contractor. The Subcontractor agrees that it is an independent contractor under this Agreement. The Subcontractor is solely responsible for, and has control over, all construction means, methods, techniques, sequences, procedures, and coordination of all portions of the Subcontract Work in accordance with the Contract Documents, unless the Contractor shall give specific written instructions concerning these matters. Further, the Subcontractor is fully responsible for, and has control over, all construction means, methods, techniques, sequences, procedures, and coordination of the Subcontract Work related to the safety of the Subcontractor's employees and any other persons working in the area of the Subcontract Work but in accordance with Contractor's safety related rules and procedures.

2.02	Storage of Materials. The Subcontractor shall examine all equipment and materials furnished by others for compliance with the Contract Documents, and thereupon unload and properly store all such equipment and material to prevent damage or loss. Contractor may deduct from payments due to Subcontractor all costs for such damage or loss resulting from improperly stored materials.

2.03	Surface and Subsurface Conditions. The Subcontractor shall inspect surface and/or subsurface conditions affecting the Subcontract Work to assure that the Subcontract Work will be properly installed in accordance with the Contract Documents. If any remedial work is required to the surface or subsurface, Subcontractor shall immediately notify Contractor in writing. SUBCONTRACTOR ACCEPTS ALL SURFACE AND SUBSURFACE CONDITIONS WHEN SUBCONTRACTOR INITIATES ITS WORK WITHOUT SUCH NOTICE, AND THE INITIATION OF WORK WITHOUT SUCH NOTICE CONSTITUTES A WAIVER OF ANY CLAIMS FOR EXTRA COMPENSATION FOR INITIAL WORK OR REPLACEMENT WORK SUBSEQUENTLY REQUIRED.

2.04	Protection of Work. Subcontractor shall take necessary precautions to properly protect the Subcontract Work and the work of the Contractor and other subcontractors. The Subcontractor shall promptly repair any damage to the work of the Contractor or other subcontractor caused by performance of the Subcontract Work; and if the Subcontractor fails to promptly repair such damage, the Contractor may deduct the costs of such repairs from payments due to Subcontractor.

2.05	Inspection of Work. The Subcontractor shall provide sufficient, safe, and proper facilities at all times for the inspection of the Subcontract Work by the Contractor or its authorized representatives. Work not meeting the specifications or intent of the Contract Documents shall be removed or rebuilt to conform to same at Subcontractor's expense.

2.06	Cleanup. The Subcontractor shall keep the Project site clean at all times of debris arising out of the performance of the Subcontract Work. If the Subcontractor shall fail to remove construction debris as instructed by Contractor, Contractor may proceed to perform such duties, and may deduct all costs of such performance from payments due to Subcontractor.

ARTICLE III

TIME, SCHEDULES AND DELAYS

3.01	Time. Time is of the essence to this Agreement. Subcontractor shall begin work as soon as instructed by the Contractor and shall prosecute the Subcontract Work promptly, efficiently, and in a manner that will not cause delay in the progress of Contractor's work or other work performed on the Project by other subcontractors. EXCEPT AS PROVIDED IN SECTION 3.02, SUBCONTRACTOR SHALL PERFORM ALL SUBCONTRACT WORK WITHIN THE NUMBER OF DAYS SHOWN ON THE PROJECT SCHEDULE OR AS OTHERWISE REQUIRED BY THE CONTRACT DOCUMENTS (the last of which days being referred to herein as the "Completion Date").

3.02	Project Schedule. Subcontractor shall perform all Subcontract Work pursuant to the Project Schedule provided by the Contractor, unless Subcontractor notifies Contractor within three (3) calendar days from receipt of the Project Schedule or revised Project Schedule that the Subcontract Work cannot be performed within the time provided in the Project Schedule. Contractor may, from time to time, reschedule the order of the Subcontract Work or otherwise revise the Project Schedule. SUBCONTRACTOR AGREES TO COMPLY WITH SUCH SCHEDULE REVISIONS WITHOUT ANY INCREASE TO THE SUBCONTRACT PRICE FOR DELAYS. Subcontractor further agrees that there will be no increase to the subcontract price for acceleration if acceleration is required due to delay in performance by the Subcontractor.

3.03	Performance Reports. Subcontractor shall furnish periodic progress reports of the Subcontract Work as may be reasonably required by Contractor, and shall attend periodic conferences at the jobsite to discuss progress at Contractor's request. Subcontractor recognizes and stipulates that failure to furnish periodic progress reports of the Subcontract Work and failure to attend periodic progress conferences at the jobsite will result in a probable loss to the Contractor, but that damages resulting from such failure could be determined only with great difficulty, or not at all. Hence, Subcontractor and Contractor stipulate and agree that (i) the "Progress Report Liquidated Damage Amount" (herein so called), listed on Page 1, above, and the "Progress Conference Liquidated Damage Amount" (herein so called), also listed on Page 1, above, are the Contractor's and Subcontractor's reasonable estimates of the probable loss that would be sustained by Contractor as a result of such failures; and (ii) that the Progress Report Liquidated Damage Amount and the Progress Conference Liquidated Damage Amount are not, and are not intended as, a penalty. If Subcontractor fails to furnish a periodic progress report, Subcontractor shall pay to Contractor within seven (7) days of Contractor's demand the Progress Report Liquidated Damage Amount for each unfurnished report. If Subcontractor fails to attend a periodic progress conference, Subcontractor shall pay to Contractor within seven (7) days of Contractor's demand the Progress Conference Liquidated Damage Amount for each unattended conference. If Subcontractor fails to pay those amounts when due, the amounts may be deducted by Contractor from other amounts due to Subcontractor.

3.04	Damages for Delay. As required in Section 3.01, above, Subcontractor shall perform all Subcontract Work by the Completion Date. Subcontractor recognizes and stipulates that, if the Subcontract Work is completed, failure to complete same on or by the Completion Date will result in a probable loss to the Contractor, but that damages resulting from such delay could be determined only with great difficulty, or not at all. Hence, Subcontractor and Contractor stipulate and agree that (i) the "Delay Liquidated Damage Amount" (herein so called), listed on Page 1, above, is the Contractor's and Subcontractor's reasonable estimate of the probable loss that would be sustained by Contractor as a result of such delay; and (ii) that the Delay Liquidated Damage Amount is not, and is not intended as, a penalty. If Subcontractor completes the Subcontract Work, but fails to complete same on or by the Completion Date, Subcontractor shall pay to Contractor within seven (7) days of Contractor's demand the Delay Liquidated Damage Amount for each day that elapses after the scheduled Completion Date in which the Subcontract Work is not completely performed. If the Subcontract Work is never completed, the Delay Liquidated Damage Amount shall not apply, and Contractor shall be entitled to seek whatever damages or remedies to which it may be entitled as a result of Subcontractor's breach.

3.05	Time Extensions. CONTRACTOR SHALL NOT BE LIABLE TO SUBCONTRACTOR FOR DELAYS, HINDRANCES, OR INTERRUPTIONS TO THE SUBCONTRACT WORK CAUSED BY THE ACT, NEGLECT, OR DEFAULT OF THE OWNER OR BY REASON OF FIRE OR OTHER CASUALTY, OR ON ACCOUNT OF RIOTS OR STRIKES, OR ON ACCOUNT OF ANY ACTS OF GOD, OR ON ACCOUNT OF ANY OTHER CAUSES BEYOND THE CONTRACTOR'S CONTROL OR ANY CIRCUMSTANCES CAUSED OR CONTRIBUTED TO BY ANY OTHER SUBCONTRACTOR OR ANY OTHER PARTY PERFORMING A PART OF THE WORK; but Contractor will cooperate with Subcontractor to enforce any just claim against the Owner for delay. Contractor shall be reimbursed by Subcontractor upon demand for any expenses, including court costs and attorney's fees, incurred in connection with any claims asserted at the request of Subcontractor. Should Subcontractor be delayed in performing the Subcontract Work by Contractor, then Subcontractor's sole and exclusive remedy against Contractor shall be an extension of time for completion equal to the delay caused, and then only if written claim for delay is made to Contractor within three (3) days from the time of the beginning of the delay, and SUBCONTRACTOR WAIVES AND RELEASES CONTRACTOR FROM ALL CLAIMS AND CAUSES OF ACTION AGAINST CONTRACTOR FOR DAMAGES ARISING OUT OF DELAYS, HINDRANCES, OR INTERRUPTIONS CAUSED BY CONTRACTOR, AND WAIVES ALL REMEDIES FOR SUCH DELAYS, HINDRANCES, OR INTERRUPTIONS CAUSED BY CONTRACTOR EXCEPT THE TIME EXTENSION SPECIFICALLY PROVIDED HEREIN.

ARTICLE IV

PRICE, PAYMENTS

4.01	Subcontract Price. Contractor agrees to pay to Subcontractor in the manner provided below the "Subcontractor Price" (herein so called) set forth above for performance of the Subcontract Work hereunder, subject to adjustments for changes pursuant to Article V, below.

4.02	Monthly Progress Payments.

(a)	Subcontractor shall submit to the Contractor monthly applications for payment on or before the "Monthly Payment Application Date" (herein so called), listed on Page 1, above, to enable Contractor to include such amount in its application for payment to the Owner. Payments shall be made by the Contractor as provided herein based upon the Contractor's valuation of that portion of the Subcontract Work performed by the Subcontractor and covered by the application for payment, considering the relation thereof to the "Schedule of Values" (as that term is defined in Section 10.01(c), below). In applying for payment, the Subcontractor shall submit a statement based upon the Schedule of Values. Application for payment made on account of materials not incorporated in the Subcontract Work, but delivered and suitably stored at the site, shall include evidence of payment from suppliers and shall be in accordance with the terms and conditions of the Contract Documents. Applications for payment submitted by the Monthly Payment Application Date shall be processed by the Contractor. No applications for payment will be processed and no payments will be made unless Subcontractor has submitted a sworn statement certifying the name of all Subcontractor's unpaid material men and sub-subcontractors. Contingent upon Contractor's receipt of payment for that month by the Owner, payments for each application shall be due after ten (10) Business Days of Owner's payment to Contractor for that portion of the Subcontract Work included in the application. Applications for payment shall be accompanied by completed, signed and notarized lien waivers and/or bills paid affidavit forms as may be required by Contractor or Owner. If a lien has been filed or if a claim has been made against Contractor's bond, no payment will be made by Contractor until Subcontractor has tendered to Contractor a release for each lien or claim, such release being in a form acceptable to Contractor.

(b)	Retainage often percent ( ) sums due hereunder shall be withheld until completion and acceptance of all Work to be performed under this Agreement, Payment of Retainage as per 4.03.

(c)	In the event the Contractor believes any of the conditions listed below warrant such action, the Contractor may withhold from monthly progress payments due hereunder sums deemed necessary to protect the Contractor and Owner from any losses on account of: (i) defective work not remedied; (ii) failure of the Subcontractor to pay bills for labor and/or materials furnished in connection with the Subcontract Work; (iii) inability of Subcontractor to complete the Subcontract Work for the unpaid Subcontract balance; (iv) failure of the Subcontractor to diligently prosecute the Subcontract Work such that damages for delay are likely; (v) damages to another subcontractor; or (vi) breach by the Subcontractor of any provision or obligation of this Agreement.

(d)	At Contractor's election, any payments to Subcontractor may be made by one or more joint checks payable to Subcontractor and one or more of its material men, laborers, or sub-subcontractors. Subcontractor agrees that any joint check payments to the Subcontractor and any of Subcontractor's material men, laborers, or sub-subcontractors shall constitute payment for the full amount of such joint check to the Subcontractor under this Agreement.

(e)	In the event Contractor receives notice of lien claim or bond claim by Subcontractor's material man, sub-subcontractor, or laborer, Contractor may, at Contractor's option, directly pay any such claimant. Any such direct payment to a claimant and any expenses in processing such claim and payment shall be deducted from the Subcontract Price and from any payments due to Subcontractor. Subcontractor and Contractor further agree that Contractor will incur substantial additional costs and expenses in administration of claims when a notice is received, that such costs would be difficult to ascertain, that the sum of $250.00 would be a reasonable and just compensation to Contractor for each notice received, and that $250.00 for each notice should be deducted from the Subcontract Price and from any payments due to Subcontractor, as liquidated damages for such administration.

(f)	If the Contractor fails to make payments to the Subcontractor as herein provided for any cause not the fault of the Subcontractor, after receipt of payments by the Owner for the Subcontractor's Work, then the Subcontractor may, upon seven (7) days written notice to the Contractor, stop work without prejudice to any other remedy it may have; provided, however, that Contractor's belief of the existence of any of the Conditions listed in items (i) - (vi) of paragraph (c), above, shall be deemed to be a cause the fault of Subcontractor.

4.03	Final Payment. Contractor's obligation to make final payment to Subcontractor is specifically contingent upon the following conditions, which are conditions precedent to Contractor's obligation to make final payment: (a) submittal by the Subcontractor of an affidavit that all payrolls, bills for material and equipment, and other indebtedness connected with the Subcontract Work, have been paid or otherwise satisfied; (b) submittal by the Subcontractor of lien waivers (in a form acceptable to Contractor), or bond claim waivers (in a form acceptable to Contractor) on bonded projects, indicating that all of the Subcontractor's material men, laborers, and sub-subcontractors have been fully paid and are waiving all statutory lien rights and releasing all bond claims; (c) consent of surety to final payment, if required; (d) approval by the Owner, architect, engineer, and/or Contractor of the Subcontract Work; and (e) receipt by the Contractor of all payments related to the Subcontract Work, including any retainage withheld by the Owner from the Contractor. SUBCONTRACTOR'S ACCEPTANCE OF FINAL PAYMENT SHALL CONSTITUTE A WAIVER OF ALL CLAIMS BY THE SUBCONTRACTOR RELATING TO THE SUBCONTRACT WORK OR TO THE CONTRACTOR'S WORK UNDER THE PRIME CONTRACT, BUT SHALL IN NO WAY RELIEVE THE SUBCONTRACTOR OF LIABILITY FOR THE OBLIGATIONS FOR REPLACING FAULTY OR DEFECTIVE WORK APPEARING AFTER FINAL PAYMENT. Any invoice not received within 365 days of job completion date will not be processed or honored by GSW.

ARTICLE V

CHANGES

5.01.	Changes. The Subcontractor may be ordered by the Contractor, without invalidating this Agreement, to make changes in the Subcontract Work within the general scope of this Agreement consisting of additions, deletions, or other revisions to the Subcontract Work. Subcontractor, prior to the commencement of such changed or revised work, shall promptly submit to the Contractor any claim for adjustment to the Subcontract Price or Project Schedule because of such changed or revised work.

5.02	Notice Required. SUBCONTRACTOR SHALL NOT BE ENTITLED TO ANY EXTRA COMPENSATION OR ADDITIONAL PERFORMANCE TIME FOR ANY CHANGED, REVISED, OR EXTRA WORK UNLESS THE SUBCONTRACTOR HAS GIVEN THE CONTRACTOR WRITTEN NOTICE OF A CLAIM FOR EXTRA COMPENSATION WITHIN FIVE (5) DAYS FROM THE BEGINNING OF THE EVENT FOR WHICH CLAIM IS MADE; AND FAILURE TO GIVE SUCH NOTICE WITHIN THE FIVE (5) DAY PERIOD SHALL CONSTITUTE A WAIVER OF ANY CLAIMS FOR EXTRA COMPENSATION. Subcontractor shall not perform any changed, revised, or extra work unless prior to the performance of such work, either: (i) the Contractor and Subcontractor enter into a modification changing the Subcontract Price and/or Project Schedule and/or Schedule of Values; or (ii) the Contractor, after receiving the Subcontractor's claim, provides the Subcontractor notice to proceed with the changed, revised, or extra work absent such modification.

5.03	Owner's Decision. Notwithstanding anything contained herein to the contrary, IF THE WORK FOR WHICH THE SUBCONTRACTOR CLAIMS EXTRA COMPENSATION TO BE DUE, IS DETERMINED BY THE OWNER, OR THE ARCHITECT/ENGINEER AS THE OWNER'S REPRESENTATIVE, TO BE SUCH THAT THE CONTRACTOR IS NOT ENTITLED TO ADDITIONAL COMPENSATION FOR SUCH WORK FROM THE OWNER, THE SUBCONTRACTOR SHALL WAIVE ITS RIGHT TO EXTRA COMPENSATION FOR SUCH WORK AND RELEASE THE CONTRACTOR FOR ANY LIABILITY FOR PAYMENT THEREFOR. The decision of the Owner, or the architect/engineer as the Owner's representative, shall be final with regard to whether extra compensation is due and with regard to the amount of such extra compensation.

5.04	Writing Required. All change orders, modifications, claims for adjustments, and notices contemplated in this Article V shall be in writing. Any unilateral change orders on the part of Subcontractor shall be compensated at the rate of actual time and materials plus five percent (5 %) overhead and five percent (5%) profit; provided, however, that Subcontractor shall execute a written change order reflecting same immediately upon Contractor's request, and that Subcontractor maintains and provides to Contractor records documenting the time and materials incurred for the unilateral change. No time and materials will be compensated unless this backup documentation is provided. Subcontractor agrees that it will not invoice Contractor for any Owner Directed Bilateral or Unilateral changes until Contractor has received from Owner an executed change order or other written evidence of modification. Subcontractor may then include the invoice in the next monthly application for payment.

ARTICLE VI

INSURANCE AND INDEMNITY

6.01	Insurance.

(a)	Prior to starting the Subcontract Work, the Subcontractor shall procure and maintain in force statutory workers' compensation insurance for all Subcontractor's employees at the Project site, employers liability insurance, commercial general liability insurance (including XCU coverage by subcontractors involved in utility work, excavation, mechanical, electrical and/or plumbing work) and automobile liability insurance and such other insurance, to the extent required by the Contract Documents for the Subcontract Work. Unless otherwise provided in this Agreement, the Subcontractor's commercial general and automobile liability insurance, as required by this provision, shall be written for not less than the limits of liability set forth on Exhibit "F," attached hereto and incorporated herein.

(b)	The commercial general liability policy shall contain a contractual liability endorsement, an endorsement listing the Contractor as additional insured and a products/completed operations endorsement. Commercial general liability insurance may be arranged under a single policy for the full limits required or by a combination of underlying policies with the balance provided by an excess or umbrella liability policy.

(c)	The worker's compensation policy shall contain a waiver of subrogation endorsement in favor of Contractor and its employees. If requested by Contractor, Subcontractor shall execute a joint agreement, in a form, which complies with State law, to be filed with the workers' compensation commission stating that Subcontractor is an independent contractor.

(d)	Prior to starting the Subcontract Work, the Subcontractor shall deliver to Contractor an original accord certificate of insurance acceptable to Contractor which evidences the coverage’s and the endorsements required herein and which states that the coverage’s afforded under the policies will not be canceled or terminated unless at least 30 days written notice is given to the Contractor. If Subcontractor subcontracts any portion of the Subcontract Work, Subcontractor shall deliver to Contractor for each of Subcontractor's sub-subcontractors or employee leasing companies, an original accord certificate of insurance, which evidences the coverage’s, and endorsements required herein. Upon request from Contractor, Subcontractor shall deliver a copy of all policies of insurance required herein.

(e)	Subcontractor waives any claim in its favor by way of subrogation, or otherwise, for any and all losses, injury, claims, causes of action, damages, or expenses, which are covered by Subcontractor's policies of insurance, except such rights as Subcontractor may have to the proceeds of such insurance. Subcontractor agrees to obtain endorsements of all policies to prevent invalidation based on this waiver.

6.02	Indemnification.

(a)	TO THE FULLEST EXTENT PERMITTED BY LAWS, THE SUBCONTRACTOR AGREES TO DEFEND, INDEMNIFY AND HOLD HARMLESS THE CONTRACTOR, THE OWNER, THE ARCHITECT/ENGINEER AND ALL OF THEIR RESPECTIVE AGENTS AND EMPLOYEES FROM AND AGAINST ALL CLAIMS, DAMAGES, LOSSES, AND EXPENSES, INCLUDING, BUT NOT LIMITED TO, ATTORNEY'S FEES AND COSTS OF COURT, ARISING OUT OF OR RELATING TO OR CONNECTED WITH THE PERFORMANCE, OR FAILURE IN PERFORMANCE, OF THE SUBCONTRACT WORK UNDER THIS AGREEMENT, EVEN IF ANY SUCH CLAIM, DAMAGE, LOSS, OR EXPENSE IS CAUSED IN WHOLE OR IN PART BY A NEGLIGENT ACT OR OMISSION BY THE CONTRACTOR, THE OWNER, THE ARCHITECT/ENGINEER, OR THEIR RESPECTIVE EMPLOYEES, REPRESENTATIVES, OR AGENTS. THE EXPRESSED INTENTION OF THE PARTIES IS THAT THE SUBCONTRACTOR'S INDEMNITY HEREIN WILL INDEMNIFY AND PROTECT THE CONTRACTOR, THE OWNER, AND THE ARCHITECT/ENGINEER FROM THE CONSEQUENCES OF THEIR OWN NEGLIGENCE. This indemnity shall include, but not be limited to, all claims, damages and losses which are: (i) attributable to bodily injury, sickness, disease or death, or to injury to or destruction of tangible property including the loss of use resulting there from; and (ii) caused in whole or in part by work performed by the Subcontractor or anyone directly or indirectly employed by it regardless of whether it is caused in whole or in part by a party indemnified hereunder.

(b)	In any and all claims against the Contractor or any of its agents or employees by an employee of the Subcontractor, or anyone directly or indirectly employed by it or anyone for whose acts it may be liable, the indemnification obligation under this Section 6.02 shall not be limited in any way by any limitation on the amount or type of damages, compensation, or benefits payable by or for the Subcontractor under Worker's Compensation acts, disability benefit acts, or other employee benefit acts.

(c)	The obligations of the Subcontractor under this Section 6.02 shall not extend to the liability of the architect/engineer, his or her agents or employees, arising out of: (a) the preparation or approval of maps, drawings, opinions, reports, surveys, change orders, designs, or specifications; or, (b) the giving of or failure to give directions or instructions by the architect/engineer, his or her agents or employees, providing such giving or failure to give is the primary cause of the injury or damage.

ARTICLE VII

BONDS AND WARRANTIES

7.01	Performance/Payment Bonds. If required by the Contractor, a performance bond and a payment bond in a form satisfactory to the Contractor shall be furnished in the full amount of the Subcontract Price, and the cost thereof shall be paid by Subcontractor as a change under Article V. This obligation shall continue throughout the term of this Agreement and may be required at any time during the performance of the Subcontract Work. These bonds will be furnished by an insurance company acceptable to Contractor at its sole discretion.

7.02	Conformance with Contract Documents. The Subcontractor warrants to the Owner and Contractor that all Subcontract Work shall comply with all requirements of the Contract Documents and shall be free from any and all defects due to faulty workmanship and/or materials for a period of one (1) year from the date Contractor has completed and has had accepted all of Contractor's work under the Contract with Owner. During that one (1) year period, the Subcontractor shall promptly remove, replace, correct, and/or repair any portion of the Subcontract Work that the Contractor or the Owner determines is defective or is not in compliance with the Contract Documents. The Subcontractor further agrees to execute any special guarantees as provided by the terms of the Contract Documents, prior to final payment.

7.03.	Payments of Laborers and Material men. The Subcontractor further warrants that all laborers, material men, and sub-subcontractors providing labor, equipment, or materials for the Subcontract Work will be paid such that neither the Owner, Contractor, or Owner's property will be subject to any claims, liens, or encumbrances.

ARTICLE VIII

TERMINATION

8.01	Partial Completion by Contractor. Should the Subcontractor fail at any time to supply a sufficient number of properly skilled workers and sufficient materials and equipment of the proper quality, as determined by the Contractor in its sole discretion, or fail in any respect to prosecute the Subcontract Work with promptness and diligence as determined by the Contractor in its sole discretion, or fail to promptly correct defective Work or fail in the performance of any of the subcontractor's obligations herein contained, the Contractor may, at his option without notice, provide such labor, materials and equipment and deduct the cost thereof, together with all loss or damage occasioned thereby, from any money then due or thereafter to become due to the Subcontractor under this Agreement. If such costs, loss and/or damage exceeds the money then due or thereafter to become due to Subcontractor under the Agreement, Subcontractor shall pay to Contractor the balance of such excess.

8.02	Termination. If the Subcontractor at any time shall refuse or neglect to supply sufficient properly skilled workers, or materials or equipment of the proper quality and quantity, or fail in any respect to prosecute the Subcontract Work with promptness and diligence, or cause by any action or omission the stoppage or interference with the work of the Contractor or other subcontractors, or fail in the performance of any of the covenants herein contained, or be unable to meet its debts as they mature, the Contractor may, at its option and at any time, terminate the Subcontractor's engagement hereunder by delivering written notice of termination to the Subcontractor. Thereafter, the Contractor may take possession of the Project and Subcontract Work, materials, tools, appliances, and equipment of the Subcontractor at the Project site, and through itself or others provide labor, equipment, and materials to prosecute the Subcontract Work on such terms and conditions as shall be deemed necessary. The Contractor shall deduct the cost thereof, under this Agreement. Including without restrictions thereto all charges, expenses, losses, costs, damages, and attorney's fees incurred as a result of the Subcontractor's failure to perform, from any money then due or thereafter to become due to the Subcontractor.

8.03	Termination for Convenience. The Contractor may, at its option, at any time, terminate the whole or any part of this Agreement for the convenience of the Contractor if the Contract has been terminated for the convenience of the Owner. Subcontractor agrees that upon any such termination, the Subcontractor's sole remedy shall be payment of full value for all work properly performed, plus a reasonable allowance for profit thereon, less all payments Subcontractor has previously received on account of such work performed. Such payments shall not include any anticipated or lost profits. Subcontractor agrees to waive all claims for damages, including claims for lost or anticipated profits, arising from or related to any such termination by Contractor. If Contractor's contract with the Owner is terminated for convenience, Subcontractor agrees to cooperate with the Contractor in Contractor's preparation of a settlement proposal to the Owner for payment for work performed prior to the termination. Such cooperation shall include, but not be limited to, providing Contractor with any documentation required by Contractor. Failure to so cooperate shall constitute a waiver of Subcontractor's right to compensation based on the termination.

8.04	Payments after Termination. If the Contractor so terminates the engagement of the Subcontractor hereunder, the Subcontractor shall not be entitled to any further payments under this Agreement until the Subcontract Work has been completed and accepted by the Owner and payment has been received by the Contractor. If the cost to complete the Subcontract Work (including all charges, expenses, losses, costs, demands and attorney's fees incurred as the result of the Subcontract termination) exceeds the unpaid Subcontract amount, Subcontractor shall pay to Contractor the balance of such excess.

ARTICLE IX

CLAIMS

9.01	Arbitration. Except as provided herein, all claims, disputes and other matters in question arising out of or relating to this Agreement or the breach thereof may be decided by arbitration if agreed by both parties. Arbitration shall then be in accordance with the Construction Industry Arbitration Rules of the American Arbitration Association then prevailing, with discovery matters conducted in accordance with the Texas Rules of Civil Procedure. The Arbitrator shall be selected by the Contractor from a list of arbitrators provided by the American Arbitration Association. The award rendered by the arbitration shall be final, and judgment may be entered upon the award in accordance with the Texas Arbitration Act. If the Contractor's agreement with the Owner does not provide for arbitration, this agreement to arbitrate shall not apply to: (a) a claim by either party for contribution or indemnity asserted in litigation brought by the Owner; or (b) a claim by the Subcontractor against the Contractor if the Contractor asserts said claim, in whole or in part, against the Owner in litigation in which the Subcontractor could be joined. If the arbitrability of this Agreement is contested by either party, the issue shall be submitted to a court of competent jurisdiction, and the arbitration shall be stayed until the determination by the court.

9.02	Participation by Subcontractor. In the event the Contractor and Owner or others arbitrate or litigate matters relating to this Agreement, it shall be the responsibility of the Subcontractor to assist in the preparation and presentation of the Contractor's case, to the extent the proceedings are related to the Subcontract Work under this Agreement.

9.03	Subcontractor Bound by Award. Should the Contractor enter into arbitration or litigation with the Owner or others regarding matters relating to this Agreement, the Subcontractor shall be bound by the result of the arbitration or litigation to the same degree as the Contractor.

9.04	Continued Performance. The Subcontractor shall carry on the Subcontract Work and maintain its progress during any arbitration or litigation proceedings.

ARTICLE X

ADDITIONAL OBLIGATIONS OF SUBCONTRACTOR

10.01	Additional Obligations of Subcontractor. In addition to the other engagements of the Subcontractor hereunder, Subcontractor hereby agrees that Subcontractor shall:

(a)	Not discriminate against any employee or applicant for employment because of race, creed, color, age, sex, national origin, or disability;

(b)	Not assign this Subcontract or any amounts due or to become due hereunder without the written consent of the Contractor, nor subcontract the whole of this Agreement without the written consent of the Contractor, nor further subcontract portions of this Agreement without written notification to the Contractor;

(c)	Promptly comply with the Submittal Requirements set forth in Exhibit "E", attached hereto and incorporated herein, including but not limited to the provision to Contractor of a "Schedule of Values" (herein so called), being a document listing the values allocated to the various portions of the Subcontract Work, prepared in such form and supported by such data to substantiate its accuracy as the Contractor may require;

(d)	Comply with all federal, state and local laws and ordinances relating to construction of buildings or structures, give adequate notices relating to the Subcontract Work to the proper authorities, and secure and pay for all necessary licenses or permits to carry on the Subcontract Work as described in the Contract Documents applicable to this Agreement;

(e)	Comply with federal and state laws relating to reporting and payment of federal and state payroll taxes on wages, including but not limited to, Federal income tax withholding provisions of the Internal Revenue Code, Federal Insurance Contribution Act (FICA) payments, Federal Unemployment Tax Act (FUTA) payments, and applicable state unemployment tax payments;

(f)	Comply with all federal, state and local laws including, but not limited to, the statutes and regulations promulgated pursuant to statutes related to Texas Workers' Compensation Act; Consolidation Omnibus Budget Reconciliation Act (COBRA); Immigration Reform and Control Act of 1986; Consumer Credit Protection Act; Title 3, Title 7 of the 1964 Civil Rights Act; Age Discrimination Employment Act; Employees Retirement Income Security Act (ERISA); Occupational Safety and Health Act of 1970 (OSHA), and the Construction Safety Act of 1969, and shall defend and be responsible for all citations, fines and penalties, and shall indemnify and hold Contractor and all other subcontractors harmless from any loss sustained by reason of any failure to so comply. As an independent contractor, Subcontractor is exclusively responsible for compliance with these regulations and laws and for the safety of Subcontractor's employees. Subcontractor will comply with Contractor's safety related rules and procedures maintained at the Project site for Subcontractor's review. Failure to comply with Contractor's safety related rules and procedures by Subcontractor or Subcontractor's personnel may require immediate dismissal of Subcontractor or Subcontractor's personnel from the Project site;

(g)	Maintain a qualified person (the "Authorized Representative") approved by Contractor on the job at all times the work is being performed by Subcontractor;

(h)	Comply with Contractor's drug free workplace program, including Subcontractor's cooperation in testing of employees and Subcontractor's permanent removal of employees failing tests or refusing to submit to tests; and

(i)	Provide Contractor with a completed Subcontractor Identification Sheet, in substantially the same form as that attached hereto as Exhibit "G" and incorporated herein, for both Subcontractor and every sub-subcontractor, laborer, or material man providing any portion of the Subcontract Work (and in this regard, Contractor shall have the right to withhold any payment to Subcontractor until such completed Subcontractor Identification Sheets have been submitted to Contractor).

(j)	All Wage Scale projects require the Subcontractor to supply the Contractor with weekly Certified Payroll Reports each and every week that the Subcontractor is on job site. Failure to supply Certified Payroll Reports as required could delay progress payments.

10.02	Additional Obligations of Contractor. In addition to the other engagements of the Contractor hereunder, Contractor hereby agrees that Contractor shall:

(a)	Be bound to the Subcontractor by all the obligations that the Owner assumes to the Contractor under the Contract Documents and by all the provisions thereof affording remedies and redress to the Contractor from the Owner insofar as applicable to this Subcontract; and

(b)	Not issue or give any instructions, orders, or directions directly to employees or workers of the Subcontractor other than the person(s) designated as the Authorized Representative of the Subcontractor unless the safety or well-being of said employees or workers as well as others is in jeopardy.

ARTICLE XI

MISCELLANEOUS

11.01	Notices. All notices required to be given under this Agreement shall be deemed delivered when deposited in the United States mail, first class postage prepaid, addressed to the recipient, or if transmitted by facsimile, upon transmission with confirmation of receipt, at the address and telephone numbers set forth on the signature page hereto.

11.02	Entire Agreement. This Agreement contains the entire agreement of the parties. Subcontractor agrees and acknowledges that no representations or warranties of any kind have been made by Contractor or its employees other than those expressed herein. All prior agreements respecting the subject matter hereof have been incorporated in the terms herein and are no longer of any force or effect. All modifications to this Agreement shall be in writing signed by the parties. The terms of this Agreement supersede and control over any terms in any proposal, bid, invoice, quote, or other document submitted to Contractor by Subcontractor.

11.03	Conflicts in Terms. In the event there is a conflict between the Contract Documents and any provisions of this Agreement, the terms of this Agreement shall govern.

11.04	Attorney's Fees. In the event that the Contractor is required to retain the services of an attorney to enforce this Agreement, or to defend against any cause of action, claim, or counterclaim brought by the Subcontractor on which the Subcontractor does not prevail, then the Contractor shall be entitled to recover the attorney's fees and costs which it has incurred, in addition to other remedies to which it is entitled under Texas law. In the event that the Subcontractor is required to retain the services of an attorney to enforce this Agreement and the Subcontractor prevails in asserting a valid claim under this Agreement, then the Subcontractor shall be entitled to recover attorney's fees and costs, which it has incurred in addition to other remedies to which it is entitled under Texas Law. In the event litigation is required to enforce this agreement, the venue of this action shall be in Parker County, Texas.

11.05	Non-Segregation of Facilities. All facilities and company activities are non-segregated except where necessary to provide privacy between the sexes.

11.06	Acceptance. The performance of any of the Subcontract Work by Subcontractor shall be deemed to be an acceptance and execution of this Agreement. Nonetheless, Subcontractor shall still execute and date this Agreement upon Contractor's request, and any failure to do shall constitute a default hereunder.

EXECUTED as of the date set forth below, but effective as set forth above.

CONTRACTOR:	SUBCONTRACTOR:

Greater Southwest Constructors, Inc.	Ed Parker , Inc.

Box 834	P.O. Box 1289

Weatherford, Texas 76086	Fort Worth, Texas 76101

Phone: 817-596-3513	817-332-8481

Fax: 817-596-3213	817-336-5904

By: ____________________________	By: ________________________________

Name:	Name: ______________________________

Title:	Title: _______________________________

Date:	________________________	Date: _______________________________

EXHIBIT "A"

DESCRIPTION OF SUBCONTRACT WORK

Contractor:	Greater Southwest Constructors, Inc.

Subcontractor:	Ed Parker , Inc.

Job #:	10-181

This Exhibit "A" is attached to that certain Subcontract Agreement between Greater Southwest Constructors, Inc., as Contractor, and the Subcontractor identified above, relating to the Job and Contract identified above. All defined terms in the Agreement are incorporated into this Exhibit "A".

The Subcontract work is described as follows:

PROVIDE LABOR MATERIAL AND EQUIPMENT TO INSTALL THE ELECTRICAL AS PER DIVISION 16

EXHIBIT "B"

CONTRACT DOCUMENTS

Contractor:	Greater Southwest Constructors, Inc.

Subcontractor:	Ed Parker , Inc.

Job #:	10-181

This Exhibit "B" is attached to that certain Subcontract Agreement between Greater Southwest Constructors, Inc., as Contractor, and the Subcontractor identified above, relating to the Job and Contract identified above. All defined terms in the Agreement are incorporated into this Exhibit "B".

The Contract Documents include, but are not limited to, the following:

DRAWINGS TITLED AIRCRAFT FUEL FILTER AREA UPGRADE BLDG.211 AND AIRCRAFT FUELAREA LEAK DETECTION REPLACEMENT LISTED IN THE DRAWING INDEX AS SHEETS C1,2,3,4 A1,2,3,4,5 S1,2,3,4 P1,2,3,4,5,6,7 M1 ,FP1,2,3,4 FA1,2 E1,2,3,4 ME1,2 THE TECHNICAL PROVISIONS FOR PROJECT NO. H24-0605&G-1530 AND ADDENDUMS 1,2,3

EXHIBIT "C"

SPECIAL PROVISIONS

Contractor:	Greater Southwest Constructors, Inc.

Subcontractor:	Ed Parker , Inc.

Job #:	10-181

This Exhibit "C" is attached to that certain Subcontract Agreement between Greater Southwest Constructors, Inc., as Contractor, and the Subcontractor identified above, relating to the Job and Contract identified above. All defined terms in the Agreement are incorporated into this Exhibit "C".

The following Special Provisions apply to this Agreement:

EXHIBIT "D"

WORKSCOPE CLARIFICATIONS

Contractor:	Greater Southwest Constructors, Inc.

Subcontractor:	Ed Parker , Inc.

Job #:	10-181

This Exhibit "D" is attached to that certain Subcontract Agreement between Greater Southwest Constructors, Inc., as Contractor, and the Subcontractor identified above, relating to the Job and Contract identified above. All defined terms in the Agreement are incorporated into this Exhibit "D".

The following Work scope Clarifications apply to this Agreement:

FURNISH ALL LABOR MATERIAL AND EQUIPMENT TO INSTALL THE ELECTRICAL SCOPE OF WORK AS PER PLANS AND SPECIFICATIONS AND ALL GENERAL AND SPECIAL CONDITIONS

EXHIBIT "E"

SUBMITTAL REQUIREMENTS

Contractor:	Greater Southwest Constructors, Inc.

Subcontractor:	Ed Parker , Inc.

Job #:	10-181

Submittal Liquidated Damage Amount: $100.00

This Exhibit "E" is attached to that certain Subcontract Agreement between Greater Southwest Constructors, Inc., as Contractor, and the Subcontractor identified above, relating to the Job and Contract identified above. All defined terms in the Agreement are incorporated into this Exhibit "E".

The Contract Documents require the Subcontractor to submit some or all of the items listed below. The omission here of any item called for by the Contract Documents does not relieve the Subcontractor from the obligation to provide the Contractor with all submittals required by the Contract Document; and the list set forth below is for the Subcontractor's convenience only. All Contract Documents are available for inspection and/or copying in the office of the Contractor. The Subcontractor shall contact the Contractor immediately if there is a need to review and/or copy any of the Contract Documents. The Subcontractor should submit the number of copies set forth above of all required submittals no later than the date specified below for each submittal. Each submittal must be stamped with a section number and section name before the Owner will accept these documents. Upon the Contractor's receipt of these submittals in complete form, the Contractor will submit them to the Owner for review. Any copies of submittals returned to the Contractor will be forwarded to the Subcontractor in due time. The Job number and Contract number listed above should be included on all correspondence relating to the Project.

If Subcontractor does not submit an item listed below on or before the date set forth below for that submittal, Contractor and Subcontractor agree that Contractor will incur additional costs and expenses in administration of this Agreement, and that such costs and expenses could only be determined with great difficulty, or not at all. Accordingly, Contractor and Subcontractor stipulate and agree that (i) the Submittal Liquidated Damage Amount" (herein so called) set forth above is Subcontractor's and Contractor's reasonable estimate of the probable, daily loss that would be sustained by Contractor as a result of such delay, and (ii) that the Submittal Liquidated Damage Amount is not, and is not intended as, a penalty. If Subcontractor fails to submit a submittal item on or by the date set forth below for that item's submission, Subcontractor shall pay to Contractor within seven (7) days of Contractor's demand the Submittal Liquidated Damage Amount for each day that elapses after the date set forth below for that item, in which the submittal item is not received by Contractor. At Contractor's election, Contractor may waive this daily Submittal Liquidated Damage Amount for one, more, or all of the days in which the submittal is delinquent; however, any daily amount waived will not constitute a waiver of any future amount, which might become due.

If any submittal contains a substantial deviation from the Contract Documents, Subcontractor shall immediately notify Contractor in a separate writing of the deviation. Failure to do so will constitute a waiver by Subcontractor of any claimed right to deviate from the Contract Documents and strict compliance with the Contract Documents will be expected and required. Furthermore, Subcontractor agrees that no submittal may substantially deviate from the Contract Documents unless Contractor notifies Subcontractor in writing that such deviation is acceptable. Failure to so notify Subcontractor of acceptance of the deviation shall never constitute a waiver on the part of Contractor, but rather will constitute unequivocal proof that such deviation has not been accepted.

If a submittal is disapproved by the Owner or if it does not conform to the requirements of the Contract Documents in Contractor's opinion, Subcontractor shall conform the submittal and re-submit same within three (3) days of Contractor's notice of the disapproval or nonconformity. If the re-submitted item still is disapproved by the Owner or does not conform in Contractor's opinion, or if a conformed submittal is not re-submitted within said three-day period, the original, disapproved and/or nonconforming submittal will be deemed to have never been delivered.

The submittal items required, and the dates on which they are required to be submitted, are as follows:

Submittal Item	Date Required / Not Required

CONTRACT	Number of Submittal Copies Required:	2(TWO)

Schedule of Values	JUNE 5,2007

Certificate of Workman's Comp Insurance	JUNE 5,2007

Certificate of General Liability Insurance	JUNE 5,2007

Original Contract	JUNE 5,2007

W-9	JUNE 5,2007

Standard Form 1413	N/A

Payment and Performance Bond	N/A

Subcontractor Identification Sheet	JUNE 5,2007

PROJECT SUBMITTAL ITEMS	Number of Submittal Copies Required:	NINE (9)

Product Data/Manufacturer's Literature	JUNE 5,2007

Shop Drawings	JUNE 5,2007

List of Products with Lead Time Letters	JUNE 5,2007

Closeout Documents: CORRECT AMOUNT OF COPIES AND ITEMS TO BE SUBMITTED AS PER PLANS AND SPECIFICATIONS WITHIN TWO WEEKS OF COMPLETION OF YOUR COMPANY’S WORK SCOPE OF PROJECT.

PRODUCT DATA/SHOP DRAWINGS

SUBMITALS AS REQUIRED IN CONTRACT DOCUMENTS

EXHIBIT "F"

INSURANCE REQUIREMENTS

Contractor:	Greater Southwest Constructors, Inc.

Subcontractor:	Ed Parker , Inc.

Job #:	10-181

This Exhibit "F" is attached to that certain Subcontract Agreement between Greater Southwest Constructors, Inc., as Contractor, and the Subcontractor identified above, relating to the Job and Contract identified above. All defined terms in the Agreement are incorporated into this Exhibit "F".

Commercial General Liability:

$2,000,000	General Aggregate

$1,000,000	Products - Comp/OP AGG

$1,000,000	Personal & Adv Injury

$1,000,000	Each Occurrence

$ 50,000	Fire Damage (Any one fire)

$ 5,000	Med Exp (Any one person)

Automobile Liability:

$1,000,000	Combined Single Limit

Worker's Compensation and Employer's Liability

$500,000	EL Each Accident

$500,000	EL Disease - Policy Limit

$500,000	EL Disease - Ea Employee

GENERAL LIABILITY NEEDS TO LIST GENERAL CONTRACTOR AS ADDITIONAL INSURED. WORKERS COMPENSATION AND WAIVER OF SUBROGATION IN FAVOR OF GENERAL CONTRACTOR OR A TWCC-85 AGREEMENT BETWEEN GC AND SUBCONTRACTOR.

EXHIBIT "G"

SUBCONTRACTOR IDENTIFICATION SHEET

Contractor:	Greater Southwest Constructors, Inc.

Subcontractor:	Ed Parker , Inc.

Job #:	10-181

This Exhibit "G" is attached to that certain Subcontract Agreement between Greater Southwest Constructors, Inc., as Contractor, and the Subcontractor identified above, relating to the Job and Contract identified above. All defined terms in the Agreement are incorporated into this Exhibit "G".

Company Name:	Ed Parker , Inc.

Address:	P.O. Box 1289 Fort Worth, Texas 76101

Work Phone Number	:	817-332-8481

Fax Phone Number:	817-336-5904

Federal ID #:	_____________________________________________________________________________________

Is your Company Incorporated?	______________________________________________________________________________

Do you Carry General Liability Insurance?	_______________________________________________________________________

Do you Carry Worker's Compensation Insurance?	________________________________________________________________

Have you requested the above insurance certificates to be sent to us?	__________________________________________________

Are you an Equal Opportunity Employer?	_______________________________________________________________________

Mr. /Ms. ___________________________________ will be handling management and administrative responsibilities for this project.

Mr. /Ms. ___________________________________ will be our on-site supervisor.

Subcontractor's Printed Name:	________________________________________________________________________

Subcontractor's Signature:	______________________________________________________________________________

(Attached supplier & Sub-Subcontractor Information sheets must be completed and submitted as Attachment to Exhibit G)

SUBCONTRACTORS THAT YOU WILL USE ON THIS PROJECT:

Subcontractor's Name: _________________________________________________________________

Contact Person:	__________________________________________________________________

Telephone Number: __________________________________________________________________

Fax Number: __________________________________________________________________

Material to be purchased: _______________________________________________________________

Subcontractor's Name: _________________________________________________________________

Contact Person:	__________________________________________________________________

Telephone Number: __________________________________________________________________

Fax Number: __________________________________________________________________

Material to be purchased: _______________________________________________________________

Subcontractor's Name: _________________________________________________________________

Contact Person:	__________________________________________________________________

Telephone Number: __________________________________________________________________

Fax Number: __________________________________________________________________

Material to be purchased: _______________________________________________________________

Subcontractor's Name: _________________________________________________________________

Contact Person:	__________________________________________________________________

Telephone Number: __________________________________________________________________

Fax Number: __________________________________________________________________

Material to be purchased: _______________________________________________________________

Subcontractor's Name: _________________________________________________________________

Contact Person:	__________________________________________________________________

Telephone Number: __________________________________________________________________

Fax Number: __________________________________________________________________

Material to be purchased: _______________________________________________________________

Subcontractor's Name: _________________________________________________________________

Contact Person:	__________________________________________________________________

Telephone Number: __________________________________________________________________

Fax Number: __________________________________________________________________

Material to be purchased: _______________________________________________________________

SUBCONTRACTORS PREVIOUS DRAW RELEASE OF LIEN

Date: _____________________ Draw Request: _____________

Period Covered From: _______________ To: _______________

Company: Ed Parker , Inc.

P.O. Box 1289

Fort Worth, Texas 76101

817-332-8481 817-336-5904

OWNER:	Lockheed Martin	Fuel Filter Area Building 211

CONTRACT #: H24-0605	JOB #:	10-181 COST CODE #: 16-100-100

STATEMENT OF CONTRACT ACCOUNT:

1. Original Contract Amount	$ 299126.00

2. Approved Changes (Net) (Add/Deduct) (As per attached breakdown)	$____________

3. Adjusted Contract Amount	$___________

4. Value of Work Completed to Date: (As per attached breakdown)	$____________

5. Less Amount Retained ( )	<$____________>

6. Total Less Retainage	$____________

7. Total Previously Certified (Deduct)	<$____________>

8. AMOUNT OF THIS REQUEST	$____________

CERTIFICATE OF THE SUBCONTRACTOR:

I hereby certify that the work performed and the materials supplied to date, as shown on the above represent the actual value of accomplishment under the terms of the Contract (and all authorized changes thereto) between the undersigned and Greater Southwest Constructors, Inc. relating to the above referenced project.

I also certify that payments, less applicable retention, have been made through the period covered by previous payments received form the contractor, to (1) all my subcontractors (sub-subcontractors) and (2) for all materials and labor used in or in connection with the performance of this Contract. I further certify I have complied with Federal, State and local tax laws, including Social Security laws and Unemployment Compensation laws and Workman's Compensation laws insofar as applicable to the performance of this Contract.

Furthermore, in consideration of the payments received, and upon receipt of the amount of this request, the undersigned does hereby waive, release and relinquish all claim or right of lien which the undersigned may now have upon the premises above described except for claims or right of lien for contract and/or change order work performed to extent that payment is being retained or will subsequently become due.

Person, Firm or Corporation furnishing Labor, Materials Services and/or Equipment	Total Amount of Labor, Materials, Services and/or Equipment	Amount of Materials delivered, Work Performed and/or Services Provided to Date	Amount Paid to Date	Unpaid to date
NOTE: Include all materials delivered, work performed or services provided WHETHER OR NOT PAYMENT IS CURRENTLY DUE. In consideration for the payment requested in this Application for Payment, the undersigned SUBCONTRACTOR HEREBY RELEASES ALL MECHANIC’S LIEN RIGHTS, McGregor ACT BOND CLAIMS, MILLER ACT BOND CLAIMS, EQUITABLE LIENS, AND ALL OTHER CLAIMS FOR PAYMENT ARISING OUT OF LABOR, MATERIAL EQUIPMENT, SUBCONTRACT WORK, SERVICES, DELAYS, EXTRA WORK AND/OR CHANGES, RELATED TO THE SUBCONTRACT WORK AT THE PROJECT UNLESS SPECIFICALLY LISTED BELOW. UPON PAYMENT OF THE SUBCONTRACTOR’S APPLICATION FOR PAYMENT, THIS INSTRUMENT SHALL CONSTITUTE A FULL RELEASE OF ALL RIGHTS, CLAIMS AND DEMANDS THROUGH THE DATE OF THIS APPLICATION, EXCEPT AS LISTED BELOW:

EXECUTED on this the	day of	, 200

SUBCONTRACTOR: Ed Parker , Inc.

By:

Name:

Title:

SWORN TO AND SUBSCRIBED before me, under my official hand and seal of office on this	day of	, 200

by

Notary Public, State of

A FALSE CERTIFICATION OF BILLS PAID ON WHICH PAYMENT IS MADE, IS A CRIMINAL OFFENSE UNDER TEXAS LAW. IT IS THE PRIME CONTRACTOR’S POLICY TO REFER ALL FALSE CERTIFICATIONS TO APPROPRIATE AUTHORITIES FOR PROSECUTION

SUBCONTRACTOR'S FINAL RELEASE OF LIEN

Date: ____________________

Company: Ed Parker , Inc.

P.O. Box 1289

Fort Worth, Texas 76101

817-332-8481 817-336-5904

AMOUNT OF CONTRACT:$299126.00

Contract # H24-0605

Project: Fuel Filter Area Bldg.211

JOB #:	10-181	The undersigned Subcontractor has agreed to, and by the receipt of final payment as shown below, full settlement of all billings and invoices against Greater Southwest Constructors, Inc. for the total amount of the contract as shown above and:

(1) Release and Waiver: The Subcontractor also hereby releases and waives any and all claims of any kind whatsoever, whether against Greater Southwest Constructors, Inc. or Lockheed Martin in connection with the work performed under this contract.

(2) Certification and Indemnification: The Subcontractor hereby certifies that the contractor has paid in full or has otherwise satisfied all obligations for all materials and equipment furnished, for all work, labor and services performed, and for all known indebtedness and claims against the subcontractor for damages arising in any manner in connection with the performance of this contract for which Greater Southwest Constructors, Inc. or Lockheed Martin might in any way be held responsible, and hereby indemnifies and holds harmless Greater Southwest Constructors, Inc. and Lockheed Martin from and against any damages, losses, costs and expenses in connection with any claims by the Contractor's subcontractors.

(3) All Debts Paid Certification: the Subcontractor hereby certifies that all of the Subcontractors Material men, Laborers, and Subcontractors have been fully paid and is waving all statutory Lien rights and releasing all bond claims.

(4) Final Payment: The payment of $_______________ which includes all changes, credits, withholdings/retainage under this contract constitutes full compensation hereunder and closes out this contract.

IN WITNESS WHEREOF, this release and waiver, certification and indemnification has been executed this ____ day of ______________, 200__	.

Ed Parker , Inc.

(CORPORATE SEAL)

(If incorporated)	By: ________________________________ (OFFICER)

Title: ________________________________________

Subscribed and sworn before me this ___________ day of _______________________, 200_______.

Notary Public: _________________________________ My Commission Expires: _______________

10-181

Ed Parker , Inc.

SA 1 of 16 Initials ______ _____

SUBCONTRACT AGREEMENT

Woodrose

2013-04-29

Joe R. Jones Construction, Inc.